AI Technical Program Manager — UST

Week 1 · Exercise 2 · Answer Workbook — Kestrel Health Network / Beacon

Individual exercise. Completed against the Exercise 2 Case Pack (Kestrel / Beacon), using the same Week 1 rubric.

For: every participant. Save your own copy before you start typing.

File name for your copy: UST_AITPM_Week1_Ex2_Workbook_Girish_Babu

Used in: Week 1 Exercise 2 (individual, 3 to 4 hours). Case facts come from the Exercise 2 Case Pack; this file holds only the forms.

# Before you begin: why this document exists

### Why this step is needed

Your Week 1 work is scored by an evaluation agent that reads your submission and must quote your own words for every score. If your findings, owners, checklist and readiness statement are spread across several files, or written in a format the evaluator cannot read, you lose marks you have earned. One workbook keeps everything in one place, in the right order.

### What exactly happens in this step

You fill in six parts over the two lab sessions: the cover block, the Findings Log (M1, Day 2), the governance frame (M2, Day 2), Release-Readiness Checklist v1 (M3, Day 3), the readiness statement to the sponsor and your assumptions (M4, Day 3). At the end of Day 3 you check it and submit this file.

### The purpose of what is being done

To let you spend the lab thinking instead of formatting, and to make sure the evaluator finds every piece of evidence for your score exactly where it expects it.

### Which part of the programme architecture this builds

This is the submission file for Week 1, whose work product is Release-Readiness Checklist v1. The same structure (findings, frame, checklist, statement) is reused in later weeks, and your Checklist v1 becomes the first layer of your Week 6 capstone.

# How to use this workbook

| Do | Do not |
| --- | --- |
| Type directly into the tables. Add rows wherever you need them (in Word: right-click a row, then Insert). | Paste screenshots, images or diagrams instead of text. The evaluator can only score words it can quote. |
| Delete the grey example rows before you submit. | Write "TBD", a team name, or a role without a person where an owner is asked for. |
| Use only the people in the Scenario Pack org chart (Part A3). | Invent people, numbers or documents that the case does not contain. If you must assume something, record it in Part 6. |
| Save often, and keep a copy somewhere you can open tomorrow. | Polish the formatting. Polish earns nothing; specific, checkable content earns everything. |

# Part 1 · Cover block

| Field | Your entry |
| --- | --- |
| Candidate id | Girish Babu (U11806) |
| Week | Week 1 · Exercise 2 · Release-Readiness Checklist v1 (Beacon) |
| Domain track used | Healthcare (Kestrel Health Network) |
| Did you use your own live project instead of the case? | No |
| AI tool(s) used | Claude (Anthropic) |
| Partner | N/A — individual exercise |
| Peer reviewer | N/A — individual exercise |
| Attempt number | 1 |
| Date submitted | 10/30/2026 |

# Part 2 · Findings Log

Record every weakness in Beacon checklist v0.9 that would stop a careful stranger trusting that Beacon is ready. Aim for 15 or more findings, with at least one for each of the five dimensions. Each finding also states which rollout phase it affects: Pilot (Riverside and Hillcrest, 14 Dec 2026) or Network (all nine hospitals, 11 Jan 2027).

Category: use one or more of Dimension gap · Ownership · AI control · Stage gate · Evidence · Contradiction; followed by the dimension, criticality (Critical / High / Medium / Low) and phase. Evidence reference: the Case Pack part and item, for example "E1 footer", "E4, 26 Nov message" or "Part B #10".

| # | v0.9 item(s) | Finding (what is wrong) | Category | Why it matters (for the sponsor) | Evidence reference | What v1 must contain instead |
| --- | --- | --- | --- | --- | --- | --- |
| F1 | #11; none (missing) | There is no Kestrel clinical safety case. Item 11 "Clinical safety case signed" points to hazard log v2, which was written and signed by Corvid AI's CSO for CorvidBench deployments, and the item owner is Neha Sharma, not Kestrel's CSO. The hazard log has no hazards for automated replies to patients, mixed-language messages or nurse queue capacity. Dr. Helen Mathews: "I have not been asked to review it." | Dimension gap; Contradiction · Dimension: Governance · Critical · Phase: Pilot | Beacon would influence patient care without the Kestrel safety case CSS-1 requires, and the three hazards most specific to Kestrel patients are not even listed. | Part B #11; E7; E2; A4 CSS-1; A3 Dr. Helen Mathews | A Kestrel clinical safety case and hazard log that cover automated replies, mixed-language under-triage and nurse queue capacity, owned and signed by Dr. Helen Mathews |
| F2 | None (missing); #26 | No line checks automated self-care replies against PCS-3. The replies read at Grade 11 (sample of 200) against a Grade 8 maximum, and they are produced in English only, while patients write in English, Hindi, Marathi or a mix. | Dimension gap · Dimension: Business · Critical · Phase: Pilot | Patients would receive health advice they may not understand, in a language they did not choose, which breaks Kestrel's own communication standard. | E1 "Reading level … Grade 11"; A1; A4 PCS-3; E8 item 26 | A reply-standard row: reading level Grade 8 or below on a tested sample, offered in English, Hindi and Marathi, with the AI-drafted disclosure, approved before replies are switched on |
| F3 | None (missing); #25 | No route exists for a patient who replies to a self-care message saying they are getting worse. Today the reply lands in the general inbox, which is answered within 48 hours. | Dimension gap · Dimension: Operational · Critical · Phase: Pilot | A patient whose condition worsens after an automated self-care reply could wait two days for a human, which is a direct patient-harm path. | E4, 3 Dec (Sunil Bhat); E8 item 25 | A rule that sends any patient reply to an automated message back to the nurse queue with urgent handling, plus contact-centre scripts for "my symptoms are worse" |
| F4 | None (missing); #17 | No line checks nurse capacity against the human-review promise. On nights, 2 triage nurses cover both pilot sites and the ward phone line. The urgent queue peaks at about 25 cases between 7 and 10 pm, which at about 6 minutes a case is 75 minutes to clear, against the 30 minutes in item 17. The threshold was lowered to shrink the queue rather than adding staff. | Dimension gap; Contradiction · Dimension: Operational · Critical · Phase: Pilot | Urgent patients could wait more than twice as long as promised at the busiest time of the night. | E4, 1 Dec (Priyanka Das); Part B #17; E3 threshold comment | A nurse capacity plan and night roster that meets the human-review time limit at the 7–10 pm peak, approved by Priyanka Das |
| F5 | #1; #3 | Intent no longer matches the product. beacon/intent.md (August) covers GP referral letters only. Patient-portal messages and automated replies were added on 9 October by a decision in the team channel, and intent.md was never updated. The August business case predates that scope. | Dimension gap; Stage gate · Dimension: Business · High · Phase: Pilot | The two riskiest capabilities, patient messages and automated replies, were never approved as intended outcomes by anyone with authority. | A5 Intent row; Part B #1 and #3 | intent.md updated for portal messages and automated replies, with outcome measures, re-approved by Dr. Anjali Rao |
| F6 | #28; #30; appendix | The pilot has no stated success measures and no abort criterion. Nothing says what the pilot must show (under-triage rate, nurse response times, patient replies) before the network rollout, or when Beacon must be switched off. | Dimension gap; Stage gate · Dimension: Business · High · Phase: Pilot; Network | The sponsor cannot tell whether the pilot worked or when to stop it, so the January decision would rest on opinion. | Part B #28, #30 and appendix note 4 | Pilot success measures, an abort criterion and a pilot exit report, approved by Dr. Anjali Rao |
| F7 | None (missing) | Nobody has checked whether the self-care advice Beacon drafts is clinically safe. ev-118 measured only the reading level of 200 replies, not whether the advice was right for the symptoms. | Dimension gap; AI control · Dimension: Quality · Critical · Phase: Pilot | Patients could be told to manage at home a symptom that needs care, with no clinician ever having reviewed what Beacon says. | E1 reading-level row; A2 step 3; E7 (no hazard for automated replies) | A clinician-reviewed sample of self-care replies with a pass mark, approved by Dr. Helen Mathews |
| F8 | #8; #9 | Items 8 and 9 are owned by Jonas Weber, the former QA Lead, who left Kestrel on 16 October. Victor Osei has owned the test strategy since November. | Ownership · Dimension: Quality · High · Phase: Pilot; Network | Nobody who still works at Kestrel can answer for the regression and validation evidence. | Part B #8, #9; A3 "No longer with Kestrel" | Quality rows owned by Victor Osei |
| F9 | #4; #15; #23; appendix | "Technical items owned by Tobias until handover". Tobias Grant is a contractor whose contract ends on 18 December, four days into the pilot and before the network rollout. No handover date or successor is named. | Ownership · Dimension: Technical · High · Phase: Pilot; Network | During the pilot and for the whole network rollout, nobody would be accountable for the architecture, load or rollback. | Part B #4, #15, #23; appendix note 3; A3 Tobias Grant | A permanent named Technical Accountable, and a dated handover record from Tobias Grant before 18 December |
| F10 | #22; appendix | "Operational ownership is joint between Platform and Nursing". Item 22's owner is "Platform / Nursing (joint)", which is two teams. | Ownership · Dimension: Operational · High · Phase: Pilot; Network | When an operational problem appears at night, each side can assume the other has it. | Part B #22; appendix note 3 | One named Operational Accountable, with Responsible people named for platform and nursing |
| F11 | #18 | Risk R-17 (mixed-language under-triage, 6.8%) shows as "accepted (N. Sharma, 5 Dec)". AIP-2 allows only the CMO or the CSO to accept a clinical risk, in writing, with a review date. Neha asked for the acceptance "so we stay green for Thursday", and Owen Fletcher recorded it. | Ownership; Contradiction · Dimension: Governance · Critical · Phase: Pilot | The largest known patient-safety risk is shown as accepted by someone with no authority to accept it, which breaks AIP-2. | Part B #18; E4, 5 and 7 Dec; E1 mixed-language row; A4 AIP-2 | R-17 either mitigated, or accepted in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date, logged in the risk register |
| F12 | Appendix (stage-gate approvals) | All five stage gates (Intent, Spec, Plan, Build and Review) were approved by one person, Neha Sharma, on one day, 2 December. She runs delivery and wrote v0.9. She approved Intent while intent.md was out of date, Plan while two plans were missing, and Build while the evaluation was on an older build. | Ownership; Stage gate · Dimension: All five · High · Phase: Pilot | The gates were rubber-stamped after the fact by the team being checked, so they give the sponsor no independent assurance. | Part B appendix note 1; A5 (Intent, Plan, Build rows) | For each stage gate, an independent named approver who is not the delivery lead, approving against the named artefact |
| F13 | #10; appendix | The threshold is ticked as 0.80 "per evaluation ev-118", but the live config is 0.72. Imran lowered it on 25 November "to reduce nurse queue", with no re-evaluation ("eval numbers will be basically the same") and no CSO approval. The appendix lets Engineering tune it "operationally". | AI control; Contradiction · Dimension: Quality · Critical · Phase: Pilot | More messages are auto-routed using a number nobody has tested, and every untested one could be an urgent case sent to a booking list. This breaks AIP-2. | Part B #10 and appendix note 2; E3 auto_route_threshold; E4, 26 Nov; A4 AIP-2 | A threshold row giving metric, number, data origin, owner and below-threshold action; changes allowed only after re-evaluation on Kestrel data and Dr. Helen Mathews' approval |
| F14 | #17 | "Human review for urgent cases" covers only Urgent. It sets no time for Emergency messages, no rule for mixed-language messages despite their 6.8% under-triage, no route for patient replies, and a 30-minute target the night staffing cannot meet. | AI control · Dimension: Operational · Critical · Phase: Pilot | A genuine emergency sent through the portal at night could sit in a queue behind 25 urgent cases. | Part B #17; A2 steps 2 and 4; E1; E4, 1 and 3 Dec | A human-in-the-loop row: every trigger condition, the named receiving role, and a time limit per category that the roster can meet |
| F15 | #19; #20 | The "Beacon Drift" dashboard compares category share and mean confidence against the supplier benchmark (CorvidBench, US/UK); no Kestrel baseline is loaded. Under-triage, the safety-critical measure, is not measured at all, and no clinician sampling is scheduled. Alerts post to a 14-member chat channel that is on no on-call rota. | AI control; Contradiction · Dimension: Operational · Critical · Phase: Pilot | If Beacon starts under-triaging patients, nothing would detect it and nobody would be paged. | Part B #19, #20; E5 (all four bullets) | A drift-monitor row: under-triage measured by scheduled clinician sampling against the ev-118 Kestrel baseline, with bands, a paged named responder and a pause on breach |
| F16 | #27; #5 | Beacon calls the floating alias "corvid-med-latest". Corvid will move it to corvid-med-3.3 on 15 December, the day after pilot go-live, and calls the change "non-material". That is the supplier's claim, not an evaluation. Pinned versions are available (CTR-311, clause 9.4), but Kestrel chose the alias. Item 27 records only that Corvid gives 14 days' notice. | AI control; Contradiction · Dimension: Technical · Critical · Phase: Pilot; Network | From day two of the pilot, patients would be triaged by a model nobody at Kestrel has tested, which breaks AIP-2's re-evaluation and CSO-approval rule. | E3 model line; E4, 30 Nov (Corvid notice); E8 item 27 (CTR-311 clause 9.4); A4 AIP-2 | The model pinned to the evaluated version, and any version change gated by re-evaluation on Kestrel data plus Dr. Helen Mathews' approval |
| F17 | #9; #10; #18 | Under-triage, the measure ev-118 itself calls "safety-critical", has no acceptance limit. It is 2.1% overall, 1.6% for English-only and 6.8% for mixed-language or transliterated messages, and nobody has said what rate is acceptable. | AI control; Dimension gap · Dimension: Quality · Critical · Phase: Pilot | Without an agreed limit, nobody can say whether a 6.8% miss rate on urgent mixed-language messages is safe enough to go live. | E1 under-triage rows; A1 (patients write Hindi/Marathi mixes) | An under-triage acceptance limit, overall and per language group, set and signed by Dr. Helen Mathews |
| F18 | #17–#30 | Fourteen items are staged "Release", which is not one of the six stages, and the Release gate is "at Go/No-Go". Item 30 calls the meeting a "formality". The stage labels exist, but the deploy-stage evidence is still checked only at the end. | Stage gate · Dimension: All five · High · Phase: Pilot | Trust still depends on one meeting rather than on evidence checked at each hand-off. | Part B #17–#30; appendix note 1 | Deploy-stage criteria with their own approvers and evidence, passed before the Go/No-Go |
| F19 | Appendix (scope note); #28 | One checklist covers both phases: "Once the pilot Go/No-Go is passed, the network rollout proceeds per Rollout plan v2." There is no pilot exit gate and no network Go/No-Go, so network-only needs (nine-site load, nurse training at nine sites, the model change, Tobias leaving) are never checked. | Stage gate; Dimension gap · Dimension: All five · Critical · Phase: Network | One meeting on 10 December would commit nine hospitals in January before anyone has seen pilot results. | Part B appendix note 4; Part B #28; A2 rollout table | A separate network gate before 11 January, with its own criteria and the pilot exit report as evidence, approved by Dr. Anjali Rao |
| F20 | #3 | spec.md v3 was updated in October by Imran using a coding agent. Its clinical safety section is copied from Corvid's hazard log, and Neha approved it on 2 December with no CSO, DPO or architecture review. | Stage gate · Dimension: Governance · High · Phase: Pilot | The specification the build follows has safety content nobody at Kestrel has checked. | A5 Spec row; Part B #3 | A spec gate where Dr. Helen Mathews signs the clinical safety section and Grace Liu signs the data protection section |
| F21 | #6 | "Feature plans complete", but 2 of 11 features have no plan: automated reply drafting and threshold tuning. Imran calls them "small config features", yet these are the two that most directly decide what patients receive. | Stage gate; Contradiction · Dimension: Technical · High · Phase: Pilot | The two highest-risk features skipped the plan stage, so there is no record of what was intended or approved. | A5 Plan row; Part B #6 | An approved plan for every feature, with clinical sign-off on the two patient-affecting ones |
| F22 | #12 | "87 of 87 PRs approved" hides that 12 PRs were approved by Imran, who also wrote the prompts the coding agent used to produce them. | Stage gate; Ownership · Dimension: Technical · High · Phase: Pilot | The author approved his own work, so 12 changes reached the release with no independent human review. | A5 Review row; Part B #12 | A review gate requiring an approver independent of the prompt author, with the 12 PRs re-reviewed |
| F23 | #23 | Rollback was rehearsed only for the application container (1.4.2 to 1.3.9 in 4 minutes). The runbook does not cover the model version, the prompt version, or switching Beacon off so that all messages go to nurses. | Stage gate; Evidence · Dimension: Technical · High · Phase: Pilot | If the model misbehaves, which is the likeliest failure, there is no rehearsed way to stop it. | Part B #23; E6 | A rehearsed rollback covering model and prompt version, and a tested switch to manual triage with a time target |
| F24 | #9 | "Model validated (96% accuracy)" cites Corvid's benchmark of 48,000 US/UK primary-care messages. Kestrel's own evaluation shows 0.93 accuracy, and 6.8% under-triage on the mixed-language messages Kestrel patients actually send. | Evidence; Contradiction · Dimension: Quality · High · Phase: Pilot | The headline figure describes a different population and overstates how well Beacon works for Kestrel's patients. | Part B #9; E2; E1 | Validation evidence on Kestrel data only (an ev-run), reviewed by Victor Osei and Dr. Helen Mathews |
| F25 | #8; #9; #10 | The configuration going live has never been evaluated. ev-118 used build 1.4.0, threshold 0.80 and corvid-med-3.2. The pilot runs build 1.4.2 at 0.72 and, from 15 December, corvid-med-3.3. The regression suite green on 1.4.2 (CI #2291) "does not include the model evaluation set". | Evidence; Contradiction · Dimension: Quality · Critical · Phase: Pilot | Nobody knows how the exact system patients will meet performs. | E1 footer; E3; E4, 26 and 27 Nov, 30 Nov; Part B #8 | A Kestrel evaluation run on build 1.4.2, the live threshold and the pinned model, reviewed by Dr. Helen Mathews |
| F26 | #9; #10 | ev-118 does not report its mix of referral letters and portal messages. Only 240 of 3,000 messages (8%) are mixed-language, while portal messages are "often" mixed. It is unknown whether the evaluation set represents pilot traffic. | Evidence · Dimension: Quality · Medium · Phase: Pilot | Results on mostly English referral letters may not hold for patient-written messages. | E1 (n = 2,760 / 240); A1 | An evaluation broken down by channel and language, matched to pilot traffic |
| F27 | #4 | "Architecture approved" cites ADR-009 of 21 September. Portal messages and automated replies, which go through MedLink to patients, were added on 9 October, and there has been no architecture review since. | Evidence; Contradiction · Dimension: Technical · High · Phase: Pilot | The integration that sends messages to patients has never had an architecture review. | Part B #4; E8 item 4 | An architecture review (new ADR) covering portal messages, automated replies and MedLink, before the pilot |
| F28 | #14 | "DPIA approved" cites DPIA v1 of August, which covers referral letters only. Grace Liu: an addendum is needed "before patient messages are processed". The pilot processes patient messages. | Contradiction · Dimension: Governance · Critical · Phase: Pilot | Kestrel would process patients' own messages with no data-protection assessment of that use. | Part B #14; E4, 2 Dec (Grace Liu) | An approved DPIA addendum for portal messages and automated replies, signed by Grace Liu |
| F29 | #21 | "Audit logging enabled" logs only message_id, category and confidence. It does not log the rationale, model version, prompt version, threshold in force, automated reply text, or the nurse's decision or override. | Contradiction · Dimension: Governance · Critical · Phase: Pilot | Kestrel could not reconstruct why a patient was triaged as they were, or what they were told. | Part B #21; E3 log_fields; A4 RP-1 | A per-decision audit record with these fields, tested in staging |
| F30 | #22 | "Data retention configured": retention_days is 365. RP-1 requires patient communications and care-decision records to be kept for 8 years. | Contradiction · Dimension: Governance · Critical · Phase: Pilot | Triage decisions and patient replies would be deleted seven years early, which breaks RP-1. | Part B #22; E3 retention_days; A4 RP-1 | Retention of 8 years on every store of Beacon decisions and messages, with configuration evidence |
| F31 | #16 | Accessibility is marked "N/A — Backend service", but Beacon sends automated replies directly to patients. | Contradiction · Dimension: Quality · Medium · Phase: Pilot | Patients with access needs may be unable to read or act on the replies. | Part B #16; A2 step 3 | An accessibility review of patient-facing replies |
| F32 | #24 | "Triage nurses trained" cites "E-learning module assigned". The learning-system report of 7 December shows 11 of 29 pilot-site nurses (38%) completed. | Contradiction · Dimension: Operational · High · Phase: Pilot; Network | Most nurses receiving Beacon cases on 14 December would be untrained. | Part B #24; E8 nurse training | Completion records for all pilot-site triage nurses before the pilot, and all network nurses before 11 January |
| F33 | #25 | "Contact centre briefed" means an email with a link to the release notes. There are no call scripts and no route for patients who say their symptoms are worse. | Contradiction · Dimension: Operational · High · Phase: Pilot; Network | Patients who call about an automated reply may get no safe answer. | Part B #25; E8 contact centre (Sunil Bhat) | Contact-centre scripts and an escalation route, approved by Sunil Bhat |
| F34 | #26 | "Patient communication (AI disclosure) approved", but the evidence is "Draft with Communications". On 7 December the draft was still with Legal, in English only. | Contradiction · Dimension: Business · Critical · Phase: Pilot | Patients would receive AI-drafted messages without the disclosure PCS-3 requires, in their chosen language. | Part B #26; E8 item 26; A4 PCS-3 | Approved AI-disclosure wording in English, Hindi and Marathi, live in every automated reply |
| F35 | #15 | Load test LT-1.4.2 passed at 3× pilot volume (p95 1.8 s). This is valid for the pilot, but it says nothing about nine-hospital volume, and its owner (Tobias) leaves on 18 December. | Evidence · Dimension: Technical · Medium · Phase: Network | The network rollout could fail under load at nine sites without anyone having tested it. | Part B #15; A2 rollout table; A3 Tobias Grant | A load test at network volume before 11 January, owned by a permanent employee |
| F36 | #29; #30 | The board announcement (#29) is ticked as a readiness item, and it is being used as the reason not to slip (Marcus Bell, 4 Dec) and to "stay green" on R-17 (Neha Sharma, 5 Dec). An announcement is a commitment, not evidence of readiness. | Evidence; Contradiction · Dimension: Business · Medium · Phase: Pilot | Schedule pressure is overriding safety decisions; the sponsor needs a decision based on evidence, not the annual report. | Part B #29, #30; E4, 4 and 5 Dec | Board communication removed from readiness criteria; the Go/No-Go decided on evidence only, with any change of date communicated by Marcus Bell |

# Part 3 · Governance frame

Decide the structure of your checklist before you write it. See the Lab Kit, Section 3.

## 3a. Who owns each dimension?

Exactly one Accountable person per dimension, by name, from the org chart. One person may own two dimensions; one dimension never has two Accountables. Test each with the Saturday question: if this fails on go-live weekend, is this the person whose phone rings?

| Dimension | Accountable (one named person) | Responsible | Consulted | Informed | Why this person (one sentence) |
| --- | --- | --- | --- | --- | --- |
| Business | Marcus Bell | Neha Sharma (intent.md, rollout plan); Sunil Bhat (patient contact) | Dr. Anjali Rao (sponsor, abort criterion); Owen Fletcher (PCS-3 compliance) | Dr. Helen Mathews; Priyanka Das | He owns the business case, the budget and the board commitment to 14 December, so a Business failure is his to answer for. Dr. Anjali Rao, not Marcus, approves the Intent and Deploy gates, so the person under schedule pressure does not also approve the go-live. |
| Technical | Neha Sharma | Imran Qureshi (code, prompts, configuration); Tobias Grant (architecture, until 18 Dec only, with handover) | Kavya Nair (platform); Rahul Menon (security) | Dr. Anjali Rao; Marcus Bell | As Delivery Lead she stays through both phases, unlike Tobias Grant, whose contract ends on 18 December. Accountability is not approval: under this frame, Technical gates are approved by people other than Neha (see 3b). |
| Quality | Victor Osei | Dr. Farah Siddiqui (evaluation set, ev-runs, threshold analysis); Imran Qureshi (regression CI) | Dr. Helen Mathews (under-triage limit); Priyanka Das (nurse-consensus labels) | Neha Sharma | He has owned the test strategy since November and replaces Jonas Weber, who left on 16 October; one person now answers for regression, the Kestrel evaluation and patient-facing quality together. |
| Governance | Dr. Helen Mathews | Grace Liu (DPIA addendum, retention); Rahul Menon (security testing); Owen Fletcher (AIP-2, risk register, RP-1) | Dr. Anjali Rao (joint authority to accept clinical risk) | Marcus Bell; Neha Sharma | As Clinical Safety Officer she owns CSS-1 and, under AIP-2, is one of only two people who may accept a clinical risk or approve a model, prompt or threshold change, and Beacon's critical gaps are clinical-safety gaps; Owen Fletcher is not chosen because he cannot accept clinical risk under his own policy. |
| Operational | Kavya Nair | Priyanka Das (nurse queue, night roster, training); Sunil Bhat (contact-centre route) | Dr. Farah Siddiqui (drift baseline); Dr. Helen Mathews (drift bands) | Dr. Anjali Rao; Neha Sharma | She owns monitoring, alerting and the platform on-call rota, so she can make a drift or under-triage alert page a named person; naming her alone replaces the v0.9 "joint between Platform and Nursing", with Priyanka Das Responsible for the nurse side. |

## 3b. Where is each dimension checked? (stage-gate map)

In each cell: who approves crossing the gate, the artefact they look at, and the phase gate it belongs to. [Pilot-shadow] = gate P1, blind-shadow start on 14 Dec · [Pilot-live] = gate P2, live auto-routing of Routine referral letters · [Network] = gate N, nine hospitals, target 11 Jan 2027. Portal messages and automated replies are out of scope for both phases (see 3d). Empty cell = no gate. All six stages are used; every dimension has gates at more than one stage.

| Dimension | Intent | Spec | Plan | Build | Review | Deploy |
| --- | --- | --- | --- | --- | --- | --- |
| Business | Approver: Dr. Anjali Rao · Artefact: beacon/intent.md re-approved for the staged pilot (referral letters only; shadow then live), with outcome measures (B-01) [Pilot-shadow]. Pilot sites and business case for referral letters (B-06) [Pilot-shadow] |  | Approver: Dr. Anjali Rao · Artefact: pilot success measures, abort criterion and exit-report format (B-02) [Pilot-live] |  |  | Approver: Dr. Anjali Rao · Artefact: signed gate P1 record naming the phase started (B-03) and board scope note from Marcus Bell (B-04) [Pilot-shadow]. Approver: Dr. Anjali Rao · Artefact: signed network Go/No-Go record citing the pilot exit report (B-05) [Network] |
| Technical |  | Approver: Kavya Nair · Artefact: architecture review superseding ADR-009, covering build 1.4.2 with portal ingestion disabled, pinned model and the parallel 3.3 shadow call (T-01) [Pilot-shadow] | Approver: Dr. Helen Mathews · Artefact: approved plan for threshold tuning (T-05) [Pilot-live]. Approver: Grace Liu · Artefact: contracts CTR-311/312 with DPAs (T-11) [Pilot-shadow] | Approver: Dr. Helen Mathews · Artefact: triage-config.yaml pinned to corvid-med-3.2 (T-02) and CI change-control rule (T-04) [Pilot-shadow]. Approver: Victor Osei · Artefact: test log proving portal ingestion and automated replies are off (T-03) [Pilot-shadow] | Approver: Victor Osei · Artefact: re-review record for the 12 PRs approved by the prompt author (T-06) [Pilot-shadow]. Approver: Kavya Nair · Artefact: load test LT-1.4.2 (T-08) [Pilot-shadow] | Approver: Kavya Nair · Artefact: rollback and switch-off rehearsal log (T-07) [Pilot-live]; Tobias Grant handover record (T-10) [Pilot-shadow]; load test at nine-hospital volume (T-09) [Network] |
| Quality |  | Approver: Dr. Helen Mathews · Artefact: under-triage acceptance limit for referral letters, overall and mixed-language (Q-01) [Pilot-live] |  | Approver: Dr. Helen Mathews · Artefact: Kestrel evaluation on build 1.4.2 at 0.80 with corvid-med-3.2 (Q-02) [Pilot-live]. Approver: Victor Osei · Artefact: regression run on 1.4.2 after configuration changes (Q-03) [Pilot-shadow] | Approver: Dr. Helen Mathews · Artefact: blind-shadow results versus nurse decisions (Q-04) [Pilot-live]; corvid-med-3.3 shadow comparison (Q-05) [Network] | Approver: Dr. Helen Mathews · Artefact: pilot exit report with under-triage from clinician sampling (Q-06) [Network] |
| Governance |  | Approver: Grace Liu · Artefact: written confirmation that DPIA v1 covers the letters-only shadow and live pilot, including the 3.3 shadow call (G-04) [Pilot-shadow]. Approver: Dr. Helen Mathews · Artefact: Kestrel-authored clinical safety section of spec.md (G-08) [Pilot-live] |  | Approver: Owen Fletcher · Artefact: full audit record fields (G-05) [Pilot-shadow]. Approver: Grace Liu · Artefact: 8-year retention on every store (G-06) [Pilot-shadow] | Approver: Dr. Helen Mathews · Artefact: written determination that blind shadow does not influence care (G-01) [Pilot-shadow]; signed Kestrel safety case and hazard log (G-02) [Pilot-live]. Approver: Dr. Anjali Rao · Artefact: valid R-17 acceptance or mitigation (G-03) [Pilot-live]. Approver: Rahul Menon · Artefact: PT-2026-77 retest (G-07) [Pilot-shadow] | Approver: Dr. Helen Mathews · Artefact: safety case updated with pilot evidence and model-version decision (G-09) [Network] |
| Operational |  | Approver: Dr. Helen Mathews · Artefact: drift-monitor design with Kestrel baseline, clinician sampling, bands and auto-pause (AI-03 design) [Pilot-live] | Approver: Priyanka Das · Artefact: human-review routing rules and time limits (AI-02) and nurse capacity plan for the 7–10 pm peak (O-01) [Pilot-live] |  |  | Approver: Kavya Nair · Artefact: alerts paging the on-call rota (O-03) [Pilot-shadow]. Approver: Dr. Helen Mathews · Artefact: live drift monitor with test page and auto-pause (AI-03) [Pilot-live]. Approver: Priyanka Das · Artefact: training completion (O-02) [Pilot-live; Network]. Approver: Sunil Bhat · Artefact: contact-centre scripts (O-04) [Pilot-live; Network] |

3c. What is the 10 December pilot Go/No-Go meeting for now? (one sentence) The 10 December meeting is no longer where items are checked: Dr. Anjali Rao confirms, from the logged evidence on each Checklist v1 row, that the gates for the phase being started have already been passed and signed by their named approvers, and decides only that phase. On current evidence that means No-Go for the pilot as configured in v0.9, and a decision on the recommended blind-shadow start (gate P1); live auto-routing (gate P2) and the network rollout (gate N) are decided later at their own gates.

## 3d. Phase gates and forward plan: what must be true at each gate

Why staged (shadow first, then live): the v0.9 configuration breaks AIP-2, CSS-1, RP-1 and PCS-3, and the conditions for safe live routing cannot all be evidenced in the two and a half working days before 14 December. A blind-shadow start keeps the announced date honestly with no AI decision reaching a patient, produces Kestrel evidence on real letters before Beacon decides anything, and moves the live decision to a proper gate instead of a weekend deadline. Blind shadow: nurses triage every letter as today; Beacon's output (corvid-med-3.2 and, from 15 Dec, corvid-med-3.3) is logged for comparison and never shown to nurses or used for routing.

| Phase gate | Target date · decided by | Approver(s) | What must be true (Checklist v1 rows) | Evidence logged in | If not met |
| --- | --- | --- | --- | --- | --- |
| P1 · Pilot-shadow start: GP referral letters at Riverside and Hillcrest in blind shadow | Decided Thu 10 Dec; evidence complete by Fri 11 Dec 17:00; start Mon 14 Dec | Dr. Anjali Rao (go); Dr. Helen Mathews (clinical) | Portal ingestion and automated replies tested off (T-03); corvid-med-3.2 pinned and 3.3 on shadow path only (T-02); architecture review (T-01); change control (T-04); 12 PRs re-reviewed (T-06); Tobias Grant handover (T-10); DPIA cover confirmed (G-04); audit fields and 8-year retention (G-05, G-06); CSO determination that shadow does not influence care (G-01); alerts paged (O-03); intent re-approved (B-01); board briefed (B-04); gate record signed (B-03) | Programme decision register; beacon/triage-config.yaml history; CI and test logs; DPIA register; CSS-1 safety-case register | Pilot does not start on 14 Dec; Marcus Bell informs the board; P1 re-run when rows are Met |
| P2 · Pilot-live activation: auto-routing of Routine referral letters, first at one site in daytime hours | Earliest after at least 500 shadow letters are reviewed; target week of 21 Dec | Dr. Helen Mathews (clinical); Dr. Anjali Rao (go) | Threshold 0.80 with origin and CSO approval (AI-01); human-review triggers and time limits (AI-02); drift monitor with auto-pause (AI-03); under-triage limit (Q-01); evaluation on live configuration (Q-02); shadow results within limit (Q-04); safety case signed (G-02); R-17 validly accepted or mitigated (G-03); Kestrel safety section of spec (G-08); success measures and abort criterion (B-02); threshold-tuning plan (T-05); rollback and switch-off rehearsed (T-07); capacity plan (O-01); all 29 pilot-site nurses trained (O-02); contact-centre scripts (O-04) | CSS-1 safety-case register; enterprise risk register; evaluation register; Grafana Beacon Drift; runbook §5; learning-system report | Pilot stays in blind shadow; no live routing |
| P3 · Pilot expansion: second site, then 24-hour routing | 7 days after P2 with no band breach | Dr. Helen Mathews | AI-03 bands not breached; under-triage from weekly clinician sampling within Q-01 limit; AI-02 response times met at the 7–10 pm peak | Grafana Beacon Drift; clinical sampling log; nurse queue dashboard | Stay at current site and hours; breach pauses auto-routing (AI-03) |
| N · Network gate: nine hospitals | Decided Thu 7 Jan 2027 for Mon 11 Jan 2027 | Dr. Anjali Rao | Pilot exit report (Q-06); network Go/No-Go record (B-05); nine-site load test (T-09); training at all sites (O-02); contact-centre scripts (O-04); model-version decision, 3.2 or 3.3 re-evaluated and approved (Q-05, G-09); permanent owner for Tobias Grant's items (T-10). Expected decision: blind shadow at nine hospitals, with live activation per site through the P2 criteria | Programme decision register; evaluation register; CSS-1 safety-case register | Network stays in shadow or the date moves; Marcus Bell updates the board |
| Later phase (out of scope): portal messages and automated replies | Not before gate N; separate intent and gates | Dr. Anjali Rao; Dr. Helen Mathews; Grace Liu | DPIA addendum for portal messages; PCS-3 replies (Grade 8, English/Hindi/Marathi, AI disclosure); route for "it's getting worse" replies; clinical review of self-care advice; mixed-language under-triage within limit; accessibility review; architecture review | DPIA register; CSS-1 safety-case register; Communications approvals | Remains out of scope |

# Part 4 · Release-Readiness Checklist v1

This is the scored work product. Write 25 to 40 rows. Every row needs all ten columns filled, including the Phase it gates.

## 4a. Header block

| Field | Your entry |
| --- | --- |
| Product / release | Beacon 1.4.x — AI-assisted patient triage (GP referral letters and patient-portal messages), Kestrel Health Network · Pilot 14 Dec 2026 (Riverside, Hillcrest) · Network 11 Jan 2027 (nine hospitals) |
| Checklist version | v1 · 28 October 2026 · status as at Tuesday 8 December 2026 · Girish Babu |
| Governance structure | Every criterion answers: what is enforced · what evidence exists · where it is logged · who approves |
| Accountable owners by dimension | Business: Marcus Bell · Technical: Neha Sharma · Quality: Victor Osei · Governance: Dr. Helen Mathews · Operational: Kavya Nair |
| Purpose of the 10 Dec pilot Go/No-Go meeting | The 10 December meeting is no longer where items are checked: Dr. Anjali Rao confirms, from the logged evidence on each Checklist v1 row, that the gates for the phase being started have already been passed and signed by their named approvers, and decides only that phase. On current evidence that means No-Go for the pilot as configured in v0.9, and a decision on the recommended blind-shadow start (gate P1); live auto-routing (gate P2) and the network rollout (gate N) are decided later at their own gates. |
| Phases gated (Phase column) | Pilot-shadow = gate P1, blind-shadow start on 14 Dec 2026 · Pilot-live = gate P2, live auto-routing of Routine referral letters · Network = gate N, nine hospitals, target 11 Jan 2027 (see Part 3d). Portal messages and automated replies are out of scope. |

## 4b. Criteria

Write the three AI-control rows first (Day 3 starts with a 10-minute sprint on them). Each must state: AI-01 Confidence threshold: the metric · the number · where the number came from (which data) · a named owner · what happens below it AI-02 Human-in-the-loop trigger: the condition that sends a case to a person · the named role that receives it · the time limit AI-03 Model drift monitor: what is measured · the baseline · the acceptable band · where the alert goes · who responds · the action on a breach

| ID | Stage | Phase | Dimension | Criterion (a checkable question) | Evidence required | Where logged | Accountable owner (named) | Approver | Status at 8 Dec + basis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI-01 | Spec | Pilot-live | Quality | Confidence threshold: Are the following recorded in beacon/spec.md and enforced in triage-config.yaml? Metric: Beacon's urgency-category confidence score (0–1). Number: 0.80. Origin: Kestrel evaluation ev-118 (3,000 Kestrel messages labelled by nurse consensus) and its re-run on build 1.4.2 with corvid-med-3.2 (Q-02), analysed by Dr. Farah Siddiqui. What happens below it: Beacon does not route the letter; it goes to the triage nurse queue (AI-02), as does every Emergency, Urgent or mixed-language letter whatever its score. Change rule: any change to the value is blocked until it is re-evaluated on Kestrel data and approved in writing by Dr. Helen Mathews (AIP-2), and the v0.9 note allowing Engineering to tune it is withdrawn. | Threshold rationale note (data set, date, auto-route share and under-triage at 0.80); config commit restoring 0.80 with the CSO approval reference; CI rule blocking threshold edits without approval | beacon/spec.md §Threshold; beacon/triage-config.yaml git history; evaluation register | Victor Osei | Dr. Helen Mathews | Not met — live config is 0.72, lowered 25 Nov to shrink the nurse queue with no re-evaluation and no CSO approval (E3; E4, 26 Nov); appendix lets Engineering tune it |
| AI-02 | Plan | Pilot-live | Operational | Human-in-the-loop trigger: Is it enforced in routing that a letter goes to the triage nurse queue at Riverside or Hillcrest (Priyanka Das's nurses) if ANY of these applies? (a) Category is Emergency or Urgent. (b) Confidence is below 0.80. (c) The letter is mixed-language or transliterated. (d) Category is Self-care (automated replies are off). (e) Beacon fails or cannot classify. And does a nurse act within these limits: Emergency 15 minutes, Urgent 30 minutes, everything else 1 business day? These must be measured on the queue dashboard, with any breach escalated to the nurse in charge and to Priyanka Das, and met at the 7–10 pm peak (O-01). | Approved routing plan with the trigger rules and time limits; routing configuration; staging test log showing each trigger (a)–(e) reaches the queue; nurse queue response-time report | beacon/plans/ (routing plan); beacon/triage-config.yaml; nurse queue dashboard | Kavya Nair | Priyanka Das | Not met — v0.9 #17 covers Urgent only; no time limit for Emergency; no rule for mixed-language letters or failures; the night peak takes about 75 min against 30 (E4, 1 Dec) |
| AI-03 | Deploy | Pilot-live | Operational | Model drift monitor: Is a monitor live that measures, weekly per site: (i) under-triage, from clinician review of a random sample of at least 100 auto-routed letters per site per week; (ii) share of letters in each urgency category; (iii) mean confidence; (iv) auto-route share? Baseline: the Kestrel results from the ev-118 re-run on the live configuration (Q-02), replacing CorvidBench in Grafana "Beacon Drift". Band: under-triage at or below the limit set by Dr. Helen Mathews (Q-01); category share and auto-route share within ±5 points; mean confidence within ±0.05. Alert: pages Kavya Nair's platform on-call rota and Dr. Helen Mathews, not only #beacon-alerts. Responders: the on-call engineer with the nurse in charge. On breach, or if the logged model version is not corvid-med-3.2: auto-routing pauses automatically, all letters go to nurses, an incident is opened, and routing resumes only with Dr. Helen Mathews' written approval. | Grafana monitor definitions with the Kestrel baseline and bands; clinician sampling schedule and first sample review; test-page log; auto-pause test log | Grafana "Beacon Drift"; on-call paging tool; clinical sampling log; incident register | Kavya Nair | Dr. Helen Mathews | Not met — baseline is CorvidBench, not Kestrel; under-triage is not measured and no sampling is scheduled; alerts go to a chat channel that is on no on-call rota (E5) |
| B-01 | Intent | Pilot-shadow | Business | Has beacon/intent.md been re-approved for the staged pilot? It should state: GP referral letters only; blind shadow from 14 Dec; live auto-routing only through gate P2; portal messages and automated replies out of scope. It should also state outcome measures (time to handle routine letters; nurse time saved; under-triage at or below the CSO limit) and review dates. | intent.md version with approval commit by Dr. Anjali Rao; outcome-measure definitions | beacon/intent.md git history; programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — intent.md (Aug) was never updated after the 9 Oct channel decision; v0.9 still assumes portal messages and replies; no outcome measures stated (A5) |
| B-02 | Plan | Pilot-live | Business | Are pilot success measures, an abort criterion and the exit-report format approved? Abort criterion: any confirmed under-triage of an Emergency letter by auto-routing, or an AI-03 breach not resolved within 24 hours, stops auto-routing. | Approved pilot measures and abort criterion; exit-report template | Programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — none exist in v0.9 or the evidence pack |
| B-03 | Deploy | Pilot-shadow | Business | Has Dr. Anjali Rao signed a gate P1 record for 14 Dec? It should name the phase being started (blind shadow), confirm every Pilot-shadow row is Met from logged evidence, and state that the board announcement is not a readiness criterion. | Signed gate P1 record listing the status of each Pilot-shadow row | Programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — meeting is on 10 Dec; v0.9 #30 calls it a "formality" |
| B-04 | Deploy | Pilot-shadow | Business | Before 14 Dec, has Marcus Bell told the board that the pilot starts in blind shadow on referral letters, that live routing follows only through a gate, and that portal messages come later? | Board briefing note with date | Board papers; programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — annual report p. 14 announces the 14 Dec pilot; no scope communication exists (E4, 4 Dec) |
| B-05 | Deploy | Network | Business | Is there a separate network Go/No-Go before 11 Jan, decided by Dr. Anjali Rao on the pilot exit report (Q-06), rather than the rollout proceeding automatically? | Signed network Go/No-Go record citing the exit report | Programme decision register | Marcus Bell | Dr. Anjali Rao | Not met — appendix note 4: the network rollout "proceeds per Rollout plan v2" once the pilot Go/No-Go is passed |
| B-06 | Intent | Pilot-shadow | Business | Are the pilot sites and the business case approved for referral-letter triage? | August board paper; September executive minutes | Board papers; executive minutes | Marcus Bell | Dr. Anjali Rao | Met — business case approved by board paper in Aug, and Riverside and Hillcrest agreed in Sep executive minutes (v0.9 #1, #2) |
| T-01 | Spec | Pilot-shadow | Technical | Is there a current architecture review, superseding ADR-009, that covers build 1.4.2 with portal ingestion disabled at MedLink, the pinned model, and the parallel corvid-med-3.3 shadow call? | New ADR with reviewer and date | Architecture decision records (beacon/adr/) | Neha Sharma | Kavya Nair | Not met — ADR-009 is dated 21 Sep, before the 9 Oct scope change; no later review (E8) |
| T-02 | Build | Pilot-shadow | Technical | Is triage-config.yaml set to corvid-med-3.2 rather than corvid-med-latest, with the CTR-311 pinned-version option active before 15 Dec, and can corvid-med-3.3 be called only on the shadow path, whose output cannot route? | Config commit; Corvid confirmation of pinned version; shadow-path test log | beacon/triage-config.yaml git history; contract register (CTR-311) | Neha Sharma | Dr. Helen Mathews | Not met — model is the floating alias, moving to corvid-med-3.3 on 15 Dec (E3; E4, 30 Nov; E8 item 27) |
| T-03 | Build | Pilot-shadow | Technical | Are portal ingestion (at MedLink and in config) and automated replies switched off, and does a test log prove that no portal message reaches Beacon and no automated reply can be sent? | Config diff; integration test log; MedLink configuration confirmation | beacon/triage-config.yaml git history; CI and test logs | Neha Sharma | Victor Osei | Not met — auto_reply_enabled: true and the pilot configuration includes portal messages (E3; A2) |
| T-04 | Build | Pilot-shadow | Technical | Does CI block any change to the model version, prompt or threshold unless a Kestrel re-evaluation and Dr. Helen Mathews' approval are linked to it? | CI rule; change log linking each change to an ev-run and approval | CI pipeline configuration and run logs | Neha Sharma | Dr. Helen Mathews | Not met — threshold changed on 25 Nov with neither (E3); the model is set to change on 15 Dec with neither (E4, 30 Nov) |
| T-05 | Plan | Pilot-live | Technical | Does every in-scope feature have an approved plan, including "threshold tuning"? (Automated reply drafting is out of scope and must be planned before any later phase.) | Approved plan files with approver and date | beacon/plans/ | Neha Sharma | Dr. Helen Mathews | Not met — 9 of 11 plans exist; "threshold tuning" and "automated reply drafting" have none (A5) |
| T-06 | Review | Pilot-shadow | Technical | Have the 12 PRs approved by Imran Qureshi, who wrote the prompts that generated them, been re-reviewed by another engineer, and does branch protection now stop a prompt author approving the resulting PR? | Re-review records for the 12 PRs; branch-protection setting | Repository PR history | Neha Sharma | Victor Osei | Not met — 12 PRs approved by their prompt author; v0.9 #12 reports "87 of 87 approved" (A5) |
| T-07 | Deploy | Pilot-live | Technical | In staging within the last 30 days, have three things been rehearsed within 15 minutes each: rollback of the model version, rollback of the prompt version, and switch-off to full manual triage? | Rehearsal log with date, operator, versions and timings | Runbook §5 change history; pipeline logs | Neha Sharma | Kavya Nair | Not met — only the container rollback was rehearsed (1.4.2→1.3.9 in 4 min, 20 Nov); model, prompt and switch-off not covered (E6) |
| T-08 | Review | Pilot-shadow | Technical | Has a load test on build 1.4.2 passed at 3× pilot volume? | Load-test report LT-1.4.2 | Test register | Neha Sharma | Kavya Nair | Met — LT-1.4.2, 1 Dec: p95 1.8 s at 3× pilot volume (v0.9 #15) |
| T-09 | Deploy | Network | Technical | Has a load test at nine-hospital volume, including the shadow call, passed before 11 Jan, owned by a permanent employee? | Load-test report at network volume | Test register | Neha Sharma | Kavya Nair | Not met — only pilot volume tested; owner Tobias Grant leaves 18 Dec |
| T-10 | Deploy | Pilot-shadow | Technical | Before 18 Dec, has Tobias Grant handed over the architecture, load-test and rollback items to named Kestrel staff, with a dated handover record? | Signed handover record naming the successor for each item | Programme decision register | Neha Sharma | Kavya Nair | Not met — "owned by Tobias until handover", with no successor or date (appendix note 3; A3) |
| T-11 | Plan | Pilot-shadow | Technical | Are the supplier contracts and data-processing agreements signed for the model provider and the integration vendor? | CTR-311 (Corvid), CTR-312 (MedLink) and their DPAs | Contract register | Neha Sharma | Grace Liu | Met — both contracts signed; both DPAs include India data residency (v0.9 #5) |
| Q-01 | Spec | Pilot-live | Quality | Has Dr. Helen Mathews set and signed an under-triage acceptance limit for referral letters, overall and for mixed-language letters? | Signed acceptance limit | beacon/spec.md; CSS-1 safety-case register | Victor Osei | Dr. Helen Mathews | Not met — no limit exists; ev-118 shows 2.1% overall and 6.8% mixed-language under-triage, "flagged review" (E1) |
| Q-02 | Build | Pilot-live | Quality | Has the Kestrel evaluation set been re-run on the exact live configuration (build 1.4.2, threshold 0.80, corvid-med-3.2), split by channel and language, with every result within agreed limits and reviewed by the CSO? | Evaluation report naming build, model and threshold; CSO review | Evaluation register | Victor Osei | Dr. Helen Mathews | Not met — ev-118 ran on build 1.4.0; the clinical safety review is "pending"; the channel split is not reported (E1) |
| Q-03 | Build | Pilot-shadow | Quality | Is the regression suite green on build 1.4.2, and re-run after the configuration changes in T-02 and T-03? | CI run for 1.4.2; re-run after the changes | CI run logs | Victor Osei | Victor Osei | Met — CI #2291 green on 1.4.2, 27 Nov (E4, Victor Osei); re-run required after the changes |
| Q-04 | Review | Pilot-live | Quality | Before live activation, have blind-shadow results been reviewed (Beacon on corvid-med-3.2 against the nurse decision, at least 500 letters across both sites), with under-triage within the Q-01 limit? | Shadow comparison report | Evaluation register; clinical sampling log | Victor Osei | Dr. Helen Mathews | Not met — shadow not yet started (planned from 14 Dec) |
| Q-05 | Review | Network | Quality | Has corvid-med-3.3 been compared in shadow against 3.2 and the nurse decisions on the same letters, and evaluated on Kestrel data, and does it have CSO approval before it is used live anywhere? | 3.3 shadow comparison and evaluation report; CSO approval | Evaluation register | Victor Osei | Dr. Helen Mathews | Not met — 3.3 is available from 15 Dec; the only basis so far is Corvid's "non-material" claim (E4, 30 Nov) |
| Q-06 | Deploy | Network | Quality | Is there a pilot exit report signed by Victor Osei and Dr. Helen Mathews? It should give under-triage from clinician sampling, response times, nurse overrides and the sample size reached. | Pilot exit report | Programme decision register; evaluation register | Victor Osei | Dr. Helen Mathews | Not met — pilot not started |
| G-01 | Review | Pilot-shadow | Governance | Has Dr. Helen Mathews determined in writing that blind shadow does not influence care, and listed the controls that keep it blind (nurses never see Beacon output; no routing from shadow)? | Signed CSO determination | CSS-1 safety-case register | Dr. Helen Mathews | Dr. Helen Mathews | Not met — the CSO has not been asked to review Beacon (E7) |
| G-02 | Review | Pilot-live | Governance | Is there a Kestrel clinical safety case and hazard log for live routing of referral letters, owned and signed by Dr. Helen Mathews (CSS-1)? It must cover these hazards: under-triage to a booking list, mixed-language letters, nurse queue capacity, and model-version change. Corvid's hazard log may be an input only. | Signed Kestrel safety case and hazard log | CSS-1 safety-case register | Dr. Helen Mathews | Dr. Helen Mathews | Not met — v0.9 #11 cites Corvid's hazard log v2, signed by Corvid's CSO; it has none of these hazards (E7) |
| G-03 | Review | Pilot-live | Governance | Is R-17 (mixed-language under-triage) either accepted in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date, or mitigated by the AI-02 rule that sends every mixed-language letter to a nurse, and is the invalid entry corrected? | Risk register entry with authorised acceptor, date and review date, or mitigation evidence | Enterprise risk register | Dr. Helen Mathews | Dr. Anjali Rao | Not met — recorded as "accepted (N. Sharma, 5 Dec)"; AIP-2 allows only the CMO or CSO to accept (E4, 5 and 7 Dec) |
| G-04 | Spec | Pilot-shadow | Governance | Has Grace Liu confirmed in writing that DPIA v1 covers the letters-only pilot in shadow and live, including the second shadow call to Corvid, and that an addendum is required before any portal phase? | Written DPO confirmation | DPIA register | Dr. Helen Mathews | Grace Liu | Unknown — DPIA v1 covers referral letters (E4, 2 Dec), but no confirmation covers the shadow call |
| G-05 | Build | Pilot-shadow | Governance | Does every Beacon decision, live or shadow, write an audit record with: message id, category, confidence, rationale, model version, prompt version, threshold in force, routing outcome, and the nurse's decision or override? | Updated log_fields; staging extract showing every field populated | beacon/triage-config.yaml; audit log store | Dr. Helen Mathews | Owen Fletcher | Not met — log_fields is only message_id, category and confidence (E3) |
| G-06 | Build | Pilot-shadow | Governance | Is retention set to 8 years (RP-1) on every store of Beacon decisions, shadow outputs and patient correspondence? | Retention settings for each store, with the date checked | beacon/triage-config.yaml; data-retention register | Dr. Helen Mathews | Grace Liu | Not met — retention_days: 365 (E3; v0.9 #22) |
| G-07 | Review | Pilot-shadow | Governance | Has the penetration test passed on the release, with every critical finding fixed, retested and signed? | PT-2026-77 report and retest | Security findings register | Dr. Helen Mathews | Rahul Menon | Met — 1 critical finding fixed; retest passed 30 Nov; signed R. Menon (v0.9 #13) |
| G-08 | Spec | Pilot-live | Governance | Has the clinical safety section of spec.md, currently copied from Corvid, been replaced by a Kestrel-authored section for the staged pilot and signed by Dr. Helen Mathews? | Signed spec.md version | beacon/spec.md git history | Dr. Helen Mathews | Dr. Helen Mathews | Not met — section copied from Corvid's hazard log; spec v3 approved only by Neha Sharma on 2 Dec (A5) |
| G-09 | Deploy | Network | Governance | Before gate N, has Dr. Helen Mathews updated the safety case with pilot evidence and approved the model version for network use? | Updated safety case; written model-version approval | CSS-1 safety-case register | Dr. Helen Mathews | Dr. Helen Mathews | Not met — no Kestrel safety case exists yet (E7) |
| O-01 | Plan | Pilot-live | Operational | Is there an approved nurse capacity plan for both pilot sites showing the 7–10 pm peak can be cleared within the AI-02 limits, given night nurses also cover the ward phone line? | Capacity plan and night roster | Nursing roster system; programme decision register | Kavya Nair | Priyanka Das | Not met — 2 night nurses; about 25 urgent cases at about 6 min each, about 75 min against 30 (E4, 1 Dec) |
| O-02 | Deploy | Pilot-live | Operational | Have all 29 pilot-site triage nurses completed the Beacon module before live activation, and all network-site nurses before their site goes live? | Learning-system completion report | Learning management system | Kavya Nair | Priyanka Das | Not met — 11 of 29 (38%) completed by 7 Dec (E8) |
| O-03 | Deploy | Pilot-shadow | Operational | Do Beacon alerts (drift, model-version mismatch, shadow-pipeline failure) page Kavya Nair's platform on-call rota, and does the runbook have a step for "model behaving wrongly"? | Paging configuration; test-page log; runbook step | On-call paging tool; runbook §5 | Kavya Nair | Kavya Nair | Not met — alerts post to #beacon-alerts (14 members), which is on no on-call rota (E5) |
| O-04 | Deploy | Pilot-live | Operational | Does the contact centre have scripts and an escalation route for patients who call about bookings made from auto-routed letters or about worsening symptoms? | Approved call scripts and escalation route | Contact-centre knowledge base | Kavya Nair | Sunil Bhat | Not met — "briefed" was an email with a link to release notes; no scripts, no route (E8) |

IDs: B = Business, T = Technical, Q = Quality, G = Governance, O = Operational, AI = the three AI-specific controls. Stages: Intent · Spec · Plan · Build · Review · Deploy. Phase: Pilot-shadow · Pilot-live · Network (Part 3d). Status as at 8 December: Met / Not met / Unknown, with a one-line basis.

# Part 5 · Readiness statement to the sponsor

No more than half a page, addressed to Dr. Anjali Rao: the decision for 14 December (go, no-go, or go only under stated conditions), what would make it a yes, and what must be true before 11 January. Written so that it could be forwarded to a regulator unchanged.

| Heading | Your text |
| --- | --- |
| To | Dr. Anjali Rao, Chief Medical Officer — Programme Sponsor |
| What is ready | Build 1.4.2 has passed its pen test (PT-2026-77), regression (CI #2291) and a 3× pilot load test (LT-1.4.2). Supplier contracts and data agreements are signed. The pilot sites and the referral-letter business case are approved. |
| What is not ready | As configured, Beacon breaks four policies: no Kestrel safety case (CSS-1); threshold lowered to 0.72 unapproved, R-17 accepted without authority, and an unevaluated model change on 15 Dec (AIP-2); 365-day retention and a three-field audit log (RP-1); replies at Grade 11 in English only (PCS-3). Under-triage is unmeasured, the night queue misses its 30-minute promise, and 11 of 29 nurses are trained. |
| My decision for 14 December | No-Go for the pilot as configured in v0.9. |
| What would make it a yes | For your decision: Go on 14 Dec for a blind-shadow pilot (gate P1, Part 3d). Scope: referral letters only, corvid-med-3.2 pinned, threshold 0.80, portal messages and replies off. Nurses triage everything and Beacon's output is only logged. This requires every Pilot-shadow row to be Met by Fri 11 Dec 17:00. Live routing of Routine letters follows at gate P2, signed by Dr. Helen Mathews and you. |
| What must be true before 11 January | A separate network Go/No-Go on 7 Jan (gate N), based on the pilot exit report. It needs a nine-site load test, training at every site, an owner for Tobias Grant's items, and a CSO-approved model version. The likely result is shadow at nine sites, with live routing per site via P2. |
| My recommendation, and why | Shadow first, then live. It keeps the announced date, exposes no patient to an untested configuration, meets all four policies, and builds Kestrel evidence before Beacon decides anything. The board announcement is not readiness evidence; Marcus Bell should brief the board on the staged scope (B-04). |

# Part 6 · Assumptions

Anything you assumed that the case did not state, for example a tolerance figure you proposed. Leave it empty if you made no assumptions.

| # | What I assumed | Why I needed to assume it |
| --- | --- | --- |
| A1 | The P1 evidence deadline is Friday 11 December 17:00. | 13 December is a Sunday; a working-day cut-off gives a clear decision before the Monday start. |
| A2 | The August business case covers referral-letter triage, the same scope as the August intent.md (B-06). | The case does not describe the business case's content or targets. |
| A3 | The annual report announced the pilot date, not its detailed scope. | Not stated; if scope was announced, Marcus Bell's board note (B-04) must correct it explicitly. |
| A4 | Blind shadow, where nurses never see Beacon's output and nothing is routed, does not influence care under CSS-1, subject to Dr. Helen Mathews' written determination (G-01). | CSS-1 does not define shadow operation. |
| A5 | DPIA v1 covers referral letters processed by Corvid, including the second shadow call to corvid-med-3.3, subject to Grace Liu's confirmation (G-04). | DPIA v1's exact content is not given; only that it covers referral letters (E4, 2 Dec). |
| A6 | Corvid can provide a pinned corvid-med-3.2 before 15 Dec under CTR-311, at a cost Marcus Bell accepts, and give shadow access to corvid-med-3.3. | Clause 9.4 offers pinned versions at additional cost but gives no lead time or price. |
| A7 | Human-review time limits: Emergency 15 minutes, Urgent 30 minutes, everything else 1 business day (AI-02). | Only the 30-minute Urgent figure appears in the case (v0.9 #17). |
| A8 | Drift monitor: weekly clinician sample of at least 100 auto-routed letters per site; bands ±5 points on category and auto-route share, ±0.05 on mean confidence (AI-03). | The case gives no sampling size, band or cadence. |
| A9 | Under-triage limit to be set by the CSO; proposed starting point no worse than the 2.1% overall in ev-118, with mixed-language letters always sent to a nurse (Q-01, AI-02). | No acceptance limit exists in the case. |
| A10 | Gate P2 needs at least 500 shadow letters reviewed (target week of 21 Dec); gate P3 follows 7 days with no band breach; gate N is decided Thursday 7 January 2027. | The case gives no letter volumes and no network decision date. |
| A11 | The extra shadow model call fits within the 3× pilot-volume headroom of LT-1.4.2 (T-08). | The load test did not include a shadow call. |
| A12 | Rollback and switch-off target: 15 minutes, rehearsed within the last 30 days (T-07). | The case gives no target; taken from the Week 1 Lab Kit example. |
| A13 | Dr. Helen Mathews is available to act on G-01 before 11 December and on the P2 rows before live activation. | Her availability is not stated, yet she approves most gates. |
| A14 | The night urgent-queue peak is driven mainly by portal messages, so a letters-only pilot reduces it; O-01 still requires proof. | The case does not split queue volume by channel. |
| A15 | Statuses are as at Tuesday 8 December 2026, using only the evidence in the case pack. | The exercise sets today as 8 December. |

# Before you submit

Tick each box only if it is true. Every "no" is a mark you can still recover. The full self-review is in the Lab Kit, Section 10.

| Check | Done? |
| --- | --- |
| Part 1: the cover block is complete | ☒ |
| Part 2: 15 or more findings, covering all five dimensions; the example row is deleted | ☒ |
| Part 3: one named Accountable person for each dimension; no teams, no "TBD" | ☒ |
| Part 4: three separate AI-control rows (AI-01, AI-02, AI-03) with every field | ☒ |
| Part 4: every row has a stage, and all six stages are used | ☒ |
| Part 4: every row names its evidence and where it is logged | ☒ |
| Part 4: statuses match the evidence; "Not met" appears where the evidence says so | ☒ |
| Part 4: the header says the 10 Dec Go/No-Go confirms gates already passed, by phase | ☒ |
| Part 5: the readiness statement is written, in half a page or less | ☒ |
| Nothing important is only in an image or only in your head | ☒ |

Submit this file through the submission process your facilitator gives you. You have up to three attempts.